## Sheet1
Day | Hours | Progress
2019-01-24 | 8 | Building NOVA
2019-01-26 | 8 | Troubleshooting NOVA
2019-01-31 | 5 | Adding camera functionality, face idenitification
2019-02-07 | 2 | Troubleshooting NOVA
2019-02-14 | 5 | Improving NOVA face identification, troubleshooting NOVA hardware
2019-02-21 | 5 | Pause on NOVA hardware, begin neural network training: venv setup
2019-02-28 | 2 | Training neural network for sex identification
2019-03-14 | 5 | Retrain NN with more data, work on deployment of neural network
2019-03-28 | 5 | Neural network deployment, use Processing to begin communication between NN and NOVA
2019-04-04 | 5 | Neural network deployment, work on data communication between NN and NOVA
2019-04-11 | 5 | Finish data communication between NOVA and NN, work on hardware again
2019-04-18 | 5 | Troubleshoot hardware
2019-04-25 | 5 | Add additional functionality if time permits
2019-05-02 | 5 | Add additional functionality if time permits
Total Hours | 70